Site diary

Daily site report

Complete every working day, on the day. Be factual and specific. Record delays, instructions and weather even when they seem minor: they become important later.

1. Day details

| Project / site |  | Date |  |
| --- | --- | --- | --- |
| Site hours Start and finish |  | Completed by |  |
| Weather Morning / afternoon; rain start and stop times; temperature |  |  |  |
| Site conditions Wet ground, access issues, work stopped? |  |  |  |

2. Labour and trades on site

| Company / trade | No. of workers | Hours | Work area |
| --- | --- | --- | --- |

3. Work completed today

| Area / level | Work done |
| --- | --- |
| EXAMPLE Ground floor | East and south wall frames stood, plumbed and temporarily braced |

4. Deliveries, plant and delays

| Item | Supplier | Issue or delay (cause) | Time lost |
| --- | --- | --- | --- |
| EXAMPLE Roof trusses | Truss plant | Delivered 1 day late; carpenters redeployed to fascia prep | 0.5 day |

5. Instructions, visitors and inspections

Record every instruction, especially verbal ones. Confirm significant instructions in writing the same day.

| Time | From / visitor | Instruction, discussion or inspection | Follow-up (variation, RFI) |
| --- | --- | --- | --- |
| EXAMPLE 10:30 | Owner | Asked to move kitchen window 300 mm left | Variation request V07 issued |

6. Safety

| # | Check | Yes | No | Details / report reference |
| --- | --- | --- | --- | --- |
| 1 | Toolbox talk or pre-start held | ☐ | ☐ |  |
| 2 | Site inspection done | ☐ | ☐ |  |
| 3 | New workers inducted | ☐ | ☐ |  |
| 4 | Incident or injury | ☐ | ☐ |  |
| 5 | Near miss | ☐ | ☐ |  |
| 6 | Hazard reported | ☐ | ☐ |  |
| 7 | Regulator, council or certifier visit | ☐ | ☐ |  |

7. Photos and sign-off

| Photo numbers / folder |  |  |  |
| --- | --- | --- | --- |
| Notes for tomorrow |  |  |  |
| Signature |  | Date |  |